## Slide 1
Name : Eman Gomaa Mabrouk
Student ID: 21031813
Email: eman_apc88@hotmail.com
NEXT81 _ONL1_ERP8_M1d
PetroPower Refinery Digital transformation
Notes: ERP presenation

## Slide 2
Digital transformation Project
PetroPower Refinery
A RoadMap to Success…
Eman Gomaa Mabrouk
NEXT81 _ONL1_ERP8_M1d
At Digi Future Solutions, we are a leading ERP implementation partner dedicated to transforming businesses through innovative technology solutions. With a steadfast commitment to excellence, we provide tailored services that empower organizations to streamline their processes, increase efficiency, and foster growth.
At Petro Power Refinery, we are dedicated to transforming crude oil into the essential fuels and products that power our world. With decades of experience in the petroleum refining industry, we have built a robust reputation for delivering high-quality refined products that fuel economies and power industries
PetroPower Refinery
Who are we?

## Slide 3
Business Analysis
Project Initiation
Project Planning
Digital transformation Project
PetroPower Refinery
Eman Gomaa Mabrouk
NEXT81 _ONL1_ERP8_M1d
Situation Statement
Fish Bone Analysis
SWOT Analysis
SMART Goals
OKRs
Power Grid
RACI Chart
Project Charter
WBS
Gantt Chart
Budget
Risk Management Plan
Communication Plan
Critical Path
Project execution
Project closure
Kick off meeting
Project Plan

## Slide 4
Digital transformation Project
PetroPower Refinery
A petroleum refining company PetroPower, is facing significant challenges in managing its operations, supply chain, as The current systems used for finance, inventory management, maintenance and Production are causing inefficiencies and data discrepancies which leads to delays in decision-making , Inefficient resource management & Decreased Productivity.
Need: To address these challenges and streamline operations, the company has decided to implement an integrated ERP system in collaboration with Digi-Future solutions , a leading company in digitalization processes and that’s to centralize data management, improve collaboration among departments, enhance visibility into key business processes, and ultimately drive better business performance , customer satisfaction & decision making“.
Inefficient Operations
Poor Decision-Making
Lack of Real time insights
Customers dissatisfaction
Over/Under Stocking
Effect
Low Profitability & Productivity
Increase in costs
Limitation in company’s growth
Impact
Situation Statement
Eman Gomaa Mabrouk
NEXT81 _ONL1_ERP8_M1d

## Slide 5
MATERIALS
Inefficient employee data management
People
  Inadequate documentation & knowledge management
  High procurement costs
  Inefficient procurement & inventory management
Inadequate Data Visibility
  Time-consuming and error-prone manual processes
Manual Processes
  Lack of automation & workflow management
  Inadequate maintenance &asset management
  Inefficient reporting & analysis
Legacy Systems
  No single, unified system to manage all aspects of the business
Lack of Integration
  Poor Communication between Departments
  Incompatibility with modern technologies and integrations
  Limited functionality & scalability
  Outdated & unsupported systems
PROBLEM
Inefficient Operations
Poor Decision-Making
Low Profitability & Productivity
FISHBONE ANALYSIS
  Delays in order fulfillment & delivery
  Poor Data management & quality
Eman Gomaa Mabrouk
NEXT81 _ONL1_ERP8_M1d
No real time data & analytics

## Slide 6
Eman Gomaa Mabrouk
NEXT81 _ONL1_ERP8_M1d
SWOT
-Top management support
-Employees expertise in business
-Strong financial profile
-Data Inconsistencies
-Processes complexity
-Manual processes
-Resistance to change
-Large customer base
-Company’s products are strategic
-Currency fluctuations
-Changes in Market demand
& Regulations
(Taxes, Accounting Standards)
Strengths
Weaknesses
Opportunities
Threats
External Factors
Internal Factors

## Slide 7
S
M
A
R
T
Attainable
Implement an ERP system that integrates all business functions, including finance, supply chain management, and operations management
Reduce inventory costs by 15% within 12 months after successful implementation
Develop a comprehensive training program for 80% of employees to ensure a smooth transition to the new ERP system
Implement an ERP system that is compliant with industry regulations and standards
Complete the ERP implementation project within 18 months
Digital transformation Project
SPECIFIC
MEASURABLE
RELEVANT
TIMEBOUND
Eman Gomaa Mabrouk
NEXT81 _ONL1_ERP8_M1d
Goals

## Slide 8
OKRs for the project
Eman Gomaa Mabrouk
NEXT81 _ONL1_ERP8_M1d
Ensure user adoption and training
Improve data management and analytics
Standardized Process and speed up workflow within the 6 month
Increase Master data accuracy by 80% within 6 months
Develop a hand on- training for Key users for 1 month
Implement ERP system to improve operational efficiency
Increase inventory accuracy by 30% within 3 months
Develop 10 key performance indicators (KPIs) to measure operational efficiency within 3 months
Establish a support team to provide ongoing assistance to end-users.
Objective
Objective
Objective
Key Results
Key Results
Key Results
Combines GOALS & METRIC to determine Measurable outcomes

## Slide 9
Digital transformation Project
Eman Gomaa Mabrouk
NEXT81 _ONL1_ERP8_M1d
PetroPower Refinery
Stakeholders' analysis
&
Power Grid
Identification of Key Stakeholders, Their involvement and their impact on the project
Facilitates creation of tailored communication plan
Involve right PEOPLE at right TIME
Determines Stakeholders level of
Influence
Interest
Measure Level of POWER over project outcome
How Much stakeholders’ NEEDs are affected by the project

## Slide 10
PetroPower Refinery
Stakeholder | Role (Related to project) | Involvement | Impact | Power or Influence (H/M/L) | Interest (H/M/L) | Engagement
-CEO -Steering committee | -Financial Supporter Project Sponser | Makes high-level decisions; serves as team resource -provides strategic guidance | -Wants the project to succeed. No resistance. | H | H | Communicate regularly, but not daily. Ask questions and give updates.
-Business process owners -Functional team | -Project team members | -Provides Business processes and ensure system meets business requirements -Gather requirements, modules configuration. | -Invested in the project as a team member. Possible resistance if their roles are affected. -Alignment with Business Need reduce adjustment and delays | H | H | Communicate daily as project team member
-Customers -Governmantal parties | -Petro Power customers -External parties | -Can give feedback on the customer experience -Ensure system are alligned with regulations | -Some highly interested; others less so. Resistance only if affects main product specs. -Resistance if regulations are not met | H | M | Communicate as needed to inform and get feedback.
-Endusers -Training team -Support team | -Petro Power Employees training end-users before Go-Live | -End users for system -Delivers training programs to end-users | Little impact at present. ensure End users are ready to use the ERP system effectively | L | H | Not directly involved. Keep updated on progress and performance.
-Internal security team | -Petro Power internal Audit team | -ensure regulations are followed | -Little impact on their role. No resistance. | L | L | Not directly involved, but should be updated before launch

## Slide 11
Keep satisfied (high priority)
Manage closely (high effort)
Monitor (minimum effort)
Show consideration
high
low
high
low
Prioritizing stakeholders (Power grid)
Governmantal parties
End users
Training Team
Support team
CEO
Steering Committee
Business process owners
Internal security team
Power
med
Interest
med
Existing Customers

## Slide 12
Importance of RACI Chart
Defines who is responsible for what tasks during project
Ensures that everyone is aware of their responsibilities and the progress of the project.
Clarifies Roles and Responsibilities
Improves Communication
Workload Balance & Better Resources allocation
Ensure that the right people are focused on the right tasks.
Avoid overloading a single stakeholder
Project RACI Chart

## Slide 14
Project Charter
A document that consolidates all details of the project, including goals, scope, deliverables, success criteria, stakeholders, and resources.
Goals
Scope
Deliverables
Success criteria
Stakeholders
Resources
Project Charter

## Slide 15
Project
Charter

## Slide 16
Project
Charter

## Slide 17
Project
Charter

## Slide 18
Project Kick Off meeting
Eman Gomaa Mabrouk
NEXT81 _ONL1_ERP8_M1d

## Slide 19
Work Breakdown Structure
A visual tool that organizes and breaks down a project into :-Milestones , Tasks & Sub-tasks.
Project
Milestone A
Task1
Task 2
Milestone B
Task 1
Sub Task
Sub Task
Sub Task
Sub Task
Sub Task
Task 2
Sub Task
-100% Rule
-Mutually exclusive tasks

## Slide 20
Project Work Breakdown Structure

## Slide 21
Critical Path for Project

## Slide 22
Critical Path for Project
the Longest sequence of dependent tasks and their duration, to determine the Shortest time necessary to complete a project
ES
EF
LF
LS

## Slide 23
Budget Plan

## Slide 24
Gantt Chart
Visual Representation
For Tasks and Timelines
Resources allocation
To prevent team overloading
Progress Tracking
Monitor if the project is on schedule or if adjustments need to be made.
A powerful project management tool that can improve coordination, communication, and decision-making throughout the project lifecycle.
Better Communication
with Team and Stakeholders
Gantt Chart for PetroPower Refinery project
Benefits of Gantt Chart

## Slide 26
Identify
Analyze
Evaluate
Treat
Monitor & Control
Risk Management Plan
A Document that help Identify, Analyze, Evaluate, Treat and control risks throughout a project
It serves as a roadmap for how risks will be handled by Mitigation plans ,to minimize their potential impact on the project's objectives
Define
Potential risks
Assess
Impact & probability
Which risk require immediate action
Develop mitigation plans
Assign team members to track risk as they arise
Risk Management life cycle

## Slide 28
Communication Plan
A Document that outlines How Information will be shared among stakeholders throughout the project lifecycle.
It specifies the Methods, Frequency, Channels & Responsibilities for communication

## Slide 29
Training Communication Plan

## Slide 30
Project Plan

## Slide 31
Eman Gomaa Mabrouk
NEXT81 _ONL1_ERP8_M1d
1
Conduct project review & lessons learned
3
Develop plan for future enhancements and support
4
Regular Training and Development
2
Technology Upgrades and Innovations
5
Develop KPIs relevant to the ERP goals
User adoption rates.
Process efficiency improvements.
Cost reductions.
Customer satisfaction scores.
Document lessons learned from both the successes and failures during the implementation. This could include:
Best practices adopted.
Issues that occurred and how they were resolved.
Implement ongoing training programs for users to adapt to updates and new functionalities.
Post Implementation Review & Continuous improvement
Stay informed about ERP technology advancements and assess their potential benefits.
Plan for regular upgrades or migrations to newer versions or platforms as needed.

## Slide 32
Thank you for taking the time to attend this presentation and for your interest in our ERP implementation project.
We hope that this presentation has provided you with a comprehensive understanding of the project's objectives, scope, and timeline…
Eman Gomaa Mabrouk
ID:21031813
NEXT81 _ONL1_ERP8_M1d
Please find project documentation in the link below:
Drive Link