## Gantt chart
Gantt Chart
TITLE: PetroPower Digital Transformation project | [6 empty] | COMPANY NAME: |  |  |  |  | Digi Future Solutions
PROJECT MANAGER: Eman Gomaa Mabrouk | [6 empty] | CREATION DATE: |  |  |  |  | 25/12/2024
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [29 empty] | PHASE TWO | [93 empty] | PHASE THREE | [40 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18 |  |  |  |  | WEEK 19 |  |  |  |  | WEEK 20 |  |  |  |  | WEEK 21 |  |  |  |  | WEEK 22 |  |  |  |  | WEEK 23 |  |  |  |  | WEEK 24 |  |  |  |  | WEEK 25 |  |  |  |  | WEEK 26 |  |  |  |  | WEEK 27 |  |  |  |  | WEEK 28 |  |  |  |  | WEEK 29 |  |  |  |  | WEEK 30 |  |  |  |  | WEEK 31 |  |  |  |  | WEEK 32 |  |  |  |  | WEEK 33 |  |  |  |  | WEEK 34 |  |  |  |  | WEEK 35 |  |  |  |  | WEEK 36 |  |  |  |  | WEEK 37 |  |  |  |  | WEEK 38 |  |  |  |  | WEEK 39 |  |  |  |  | WEEK 40 |  |  |  |  | WEEK 41 |  |  |  |  | WEEK 42 |  |  |  |  | WEEK 43 |  |  |  |  | WEEK 44 |  |  |  |  | WEEK 45 |  |  |  |  | WEEK 46 |  |  |  |  | WEEK 47 |  |  |  |  | WEEK 48 |  |  |  |  | WEEK 49 |  |  |  |  | WEEK 50 |  |  |  |  | WEEK 51 |  |  |  |  | WEEK 52 |  |  |  |  | WEEK 53 |  |  |  |  | WEEK 54 |  |  |  |  | WEEK 55 |  |  |  |  | WEEK 56 |  |  |  |  | WEEK 57 |  |  |  |  | WEEK 58 |  |  |  |  | WEEK 59 |  |  |  |  | WEEK 60 |  |  |  |  | WEEK 61 |  |  |  |  | WEEK 62 |  |  |  |  | WEEK 63 |  |  |  |  | WEEK 64 |  |  |  |  | WEEK 65 |  |  |  |  | WEEK 66 |  |  |  |  | WEEK 67 |  | WEEK 68 | WEEK 69 | WEEK 70 | WEEK 71 | WEEK 72 | WEEK 73
[7 empty] | MARCH | [24 empty] | April | [19 empty] | MAY | [20 empty] | JUNE | [27 empty] | July | [30 empty] | Augest | [30 empty] | Septemeber | [30 empty] | October | [29 empty] | November | [29 empty] | December | [29 empty] | Januarary | [30 empty] | February
[7 empty] | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M
[7 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 23 | 24 | 25 | 26 | 27 | 27.8718 | 29.1166
1 | Exploration & Blueprint Phase | [274 empty] | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 23 | 24 | 25 | 26 | 27 | 27.8718 | 29.1166
1.1.1 | Conduct stakeholder sessions and interviews | Business Analyst | 2025-03-01 | 2025-03-08 | 6 | 0%
1.1.2 | Document business & Techincal requirements and processes | Business Analyst | 2025-03-08 | 2025-03-17 | 8 | 0%
1.2.1 | Develop system architecture and design | Techincal Team | 2025-03-17 | 2025-03-23 | 5 | 0%
1.2.2 | Identify techincal requirments and integration requirements | Techincal Team | 2025-03-23 | 2025-03-29 | 5 | 0%
1.2.3 | Identify necessary customizations and configurations | Functional Team | 2025-03-29 | 2025-04-01 | 4 | 0% | [161 empty] | PH+FM20ASE THREE
1.3.1 | Conduct sessions with stakeholders | Data Specialist | 2025-03-01 | 2025-03-05 | 5 | 0%
1.3.2 | Define data migration plan and requirements | Data Specialist | 2025-03-05 | 2025-03-18 | 10 | 0%
1.4.1 | Business Process Mapping and techincal reqyirements Blueprint | Functional Team | 2025-04-01 | 2025-04-07 | 5 | 0%
1.4.2 | Get Stakeholders approvals | Project manager | 2025-04-07 | 2025-04-08 | 2 | 0%
2 | Realization phase
2.1.1 | system installation,configuration and settings | Technical Lead | 2024-04-08 | 2024-05-05 | 20 | 0%
2.1.2 | Configure system functional modules | Functional Team | 2024-05-06 | 2024-06-08 | 25 | 0%
2.1.3 | Develop customizations and integrations | Techincal Team | 2024-06-08 | 2024-06-22 | 15 | 0%
2.2.1 | Develop tool for master data cleasing | Data Specialist | 2025-03-18 | 2025-04-28 | 30 | 0%
2.2.2 | work on data cleasing with IT team and stakeholders | Data Specialist | 2025-04-28 | 2025-08-07 | 60 | 0%
2.2.3 | Prepare Sample Upload for testing | Data Specialist | 2025-04-07 | 2025-07-17 | 10 | 0%
2.3.1 | Conduct unit testing and debugging | QA team | 2025-06-22 | 2025-07-01 | 10 | 0%
2.3.2 | Develop test plans and scripts | QA team | 2025-07-01 | 2025-07-05 | 5 | 0%
2.3.3 | Conduct system testing and quality assurance (SIT) | Fuctional team | 2025-07-17 | 2025-07-26 | 10 | 0%
2.3.4 | Identify and resolve defects | Techincal team | 2025-07-26 | 2025-07-30 | 5 | 0%
2.4.1 | Tender for hardware and data storage vendors | Procurement team | 2025-04-12 | 2025-04-22 | 10 | 0%
2.4.2 | complete Infrastructure and Hardware procurement process | Procurement team | 2025-04-22 | 2025-06-19 | 45 | 0%
3 | Final Preparation & User training
3.1.1 | Conduct user acceptance testing workshops (UAT) | Fuctional team | 2025-07-30 | 2025-08-09 | 10 | 0%
3.1.2 | Get Final approvals for (UAT) | Project manager | 2025-08-09 | 2025-08-13 | 5 | 0%
3.2.1 | Develop user manuals and training materials | Training Team | 2025-08-08 | 2025-08-21 | 15 | 0%
3.2.2 | Conduct Key-user training and support | Training Team | 2025-08-21 | 2025-09-09 | 20 | 0%
4 | Go-Live,Deployment & Post-Implentation support
4.1.1 | Finalize Cutover Plan | Project Manager | 2025-08-13 | 2025-08-17 | 5 | 0%
4.1.2 | Execute Go-Live Checklist | Project Manager | 2025-08-17 | 2025-08-21 | 5 | 0%
4.2.1 | System deployment to production | Techincal team | 2025-09-09 | 2025-09-18 | 10 | 0%
4.2.2 | Master data and opening balances upload | Functional team | 2025-09-18 | 2025-09-22 | 5 | 0%
4.3.1 | Conduct post-go-live support and monitoring | Support team | 2025-09-23 | 2025-12-21 | 90 | 0%