## Project Budget
Budget: Project PetroPower Refinery Project | [10 empty] | TARGET BUDGET | ACTUAL/FINAL SPEND | UNDER/ OVER
[11 empty] | 1414000 | 0 | 1414000
MILESTONES & TASKS |  | LABOR |  |  |  |  | MATERIALS |  |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
|  | EMPLOYEE | HOURS | Days | RATE | Total | UNITS | $/UNIT(S) | Total | $
ID | Milestone 1: Exploration & Blueprint Phase
1.1.1 | Conduct stakeholder sessions and interviews | Business Analyst | 30 | 6 | 250 | 7500 |  |  |  |  | 7500 |  | -7500
1.1.2 | Document business requirements and processes | Business Analyst | 40 | 8 | 250 | 10000 |  |  |  |  | 10000 |  | -10000
1.2.1 | Develop system architecture and design | Techincal Team | 25 | 5 | 300 | 7500 |  |  |  |  | 7500 |  | -7500
1.2.2 | identify techincal requirments and integration requirements | Techincal Team | 25 | 5 | 300 | 7500 |  |  |  |  | 7500 |  | -7500
1.2.3 | Identify necessary customizations and configurations | Functional Team | 20 | 4 | 350 | 7000 |  |  |  |  | 7000 |  | -7000
1.3.1 | Conduct sessions with stakeholders | Data Specialist | 25 | 5 | 250 | 6250 |  |  |  |  | 6250 |  | -6250
1.3.2 | Define data migration plan and requirements | Data Specialist | 50 | 10 | 250 | 12500 |  |  |  |  | 12500 |  | -12500
1.4.1 | Business Process Mapping | Functional Team | 25 | 5 | 350 | 8750 | 10 | 3000 | 30000 |  | 38750 |  | -38750
1.4.2 | Get Stakeholders for BluePrint approvals | Project manager | 10 | 2 | 850 | 8500 |  |  |  |  | 8500 |  | -8500
|  |  | 250 |  |  | 75500 | 10 | 3000 | 30000 | 0 | 105500 | 0 | -105500
Milestone 2: Realization phase
2.1.1 | system installation,configuration and settings | Techincal Team | 100 | 20 | 300 | 30000 |  |  |  |  | 30000 |  | -30000
2.1.2 | Configure system functional modules | Functional Team | 125 | 25 | 350 | 43750 |  |  |  |  | 43750 |  | -43750
2.1.3 | Develop customizations and integrations | Techincal Team | 75 | 15 | 300 | 22500 |  |  |  |  | 22500 |  | -22500
2.2.1 | Master data cleansing by using data management tools | Data Specialist | 150 | 30 | 250 | 37500 |  |  |  |  | 37500 |  | -37500
2.2.2 | Communicate data cleasing results with IT team and stakeholders | Data Specialist | 300 | 60 | 250 | 75000 |  |  |  |  | 75000 |  | -75000
2.2.3 | Prepare Sample Upload for testing | Data Specialist | 50 | 10 | 250 | 12500 |  |  |  |  | 12500 |  | -12500
2.3.1 | Conduct unit testing and debugging | QA Team | 50 | 10 | 250 | 12500 |  |  |  |  | 12500 |  | -12500
2.3.2 | Develop test plans and scripts | QA Team | 25 | 5 | 250 | 6250 | 50 | 20 | 1000 |  | 7250 |  | -7250
2.3.3 | Conduct system testing and quality assurance (SIT) | Functional Team | 50 | 10 | 350 | 17500 |  |  |  |  | 17500 |  | -17500
2.3.4 | Identify and resolve defects | Techincal Team | 25 | 5 | 300 | 7500 |  |  |  |  | 7500 |  | -7500
2.4.1 | Infrastructure and Hardware | Procurement team | 50 | 10 | 100 | 5000 | 200 | 2000 | 400000 |  | 405000 |  | -405000
|  |  | 1000 |  |  | 270000 | 250 |  | 401000 | 0 | 671000 | 0 | -671000
Milestone 3:Final Preparation & User training
3.3 | Conduct user acceptance testing (UAT) | Functional Team | 50 | 10 | 350 | 17500 |  |  |  |  | 17500 |  | -17500
3.4 | Get Final approvals for (UAT) | Project manager | 25 | 5 | 850 | 21250 |  |  |  |  | 21250 |  | -21250
3.5 | Develop user manuals and training materials | Training Team | 75 | 15 | 300 | 22500 | 50 | 450 | 22500 |  | 45000 |  | -45000
3.6 | Conduct Key-user training and support | Training Team | 100 | 20 | 300 | 30000 |  |  |  | 25000 | 55000 |  | -55000
|  |  | 250 |  |  | 91250 | 50 |  | 22500 | 25000 | 138750 | 0 | -138750
Go-Live,Deployment & Post-Implentation support
4.1 | Finalize Cutover Plan | Project Manager | 25 | 5 | 850 | 21250 |  |  |  |  | 21250 |  | -21250
4.2 | Execute Go-Live Checklist | Project Manager | 25 | 5 | 850 | 21250 |  |  |  |  | 21250 |  | -21250
4.3 | System deployment to production | Techincal Team | 50 | 10 | 300 | 15000 |  |  |  |  | 15000 |  | -15000
4.4 | Master data and opening balances upload | Data Specialist | 25 | 5 | 250 | 6250 |  |  |  |  | 6250 |  | -6250
4.5 | Conduct post-go-live support and monitoring | Support team | 450 | 90 | 300 | 135000 |  |  |  |  | 135000 |  | -135000
|  |  | 575 |  |  | 198750 | 0 | 0 | 0 |  | 198750 |  | -198750
A | Software Licenses | - | [7 empty] | 200000 | 200000 |  | -200000
B | Miscellaneous expenses | - | [7 empty] | 50000 | 50000 |  | -50000
C | Reserve buffer | - | [8 empty] | 50000 |  | -50000
|  |  | 0 |  |  | 0 |  |  |  | 250000 | 300000 |  | -300000
TOTAL | [10 empty] | 1414000 | 0 | -1414000
Note on K34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Training Facilities, place rents.

## Summary (hidden)
| Labor Consulting services | Materials | Fixed Cost | OH | Total
Training Team | 52500 | 22500 | 25000 |  | 100000
Project Manager | 72250 |  |  |  | 72250
Business Analyst | 35000 |  |  |  | 35000
Data Specialist | 32500 |  |  |  | 32500
Functional Team | 122500 | 30000 |  |  | 152500
Techincal Team | 81000 |  |  |  | 81000
Procurement team | 7500 | 400000 |  |  | 407500
QA team | 25000 | 1000 |  |  | 26000
Support team | 135000 |  |  |  | 135000
Software Licenses |  |  | 200000 |  | 200000
Misc.& Admin Expenses |  |  |  | 50000 | 50000
Reserve buffer |  |  |  |  | 50000
| 563250 | 453500 | 225000 | 50000 | 1341750
Implementation and consulting costs | 406750
Hardware and Infrastructure | 400000
Training and support costs | 235000
Software and licensing costs | 200000
Miscellaneous costs | 50000
Reserve buffer | 50000
1341750