## WBS Spreadsheet
Project Work Breakdown Structure
Milestone |  | Task | Task ID | Sub Task | Owner | Duration (Days) | Dictionary
Exploration & Blueprint Phase Deliverable: Blueprint document | 1.1 | Requirement Gathering | 1.1.1 | Conduct stakeholder sessions and interviews | Business Analyst | 6 | Conduct sessions and interviews with stakeholders to gather business requirements and understand the current business processes.
|  |  | 1.1.2 | Document business & Techincal requirements and processes | Business Analyst | 8 | Document the business requirements and processes gathered based on the stakeholder sessions and interviews.
| 1.2 | System Design | 1.2.1 | Develop system architecture and design | Techincal Team | 5 | Develop a detailed architecture and design for the system, including the system landscape, infrastructure, and integration requirements.
|  |  | 1.2.2 | Identify techincal requirments and integration requirements | Techincal Team | 5 | Servers, network ,define how system will interact with other systems, Ex.Use of APIs for data integration with external systems data recovery plans ( ex.disaster recovery solutions)
|  |  | 1.2.3 | Identify necessary customizations and configurations | Functional Team | 4 | including the development configurations,enhancements and customized reports & processes requests
| 1.3 | Data Maintenance & Migration Plan | 1.3.1 | Conduct sessions with stakeholders | Data Specialist | 5 | to identify data size and asses data quality
|  |  | 1.3.2 | Define data migration plan and requirements | Data Specialist | 10 | Plans for data extraction, cleansing tools, transformation, and loading of data from legacy systems
| 1.4 | Blueprint Development & Signoff | 1.4.1 | Business Process Mapping and techincal reqyirements Blueprint | Functional Team | 5 | a critical step in ensuring that the new system effectively meets the organization's needs. It involves identifying, documenting, and analyzing the business processes
|  |  | 1.4.2 | Get Stakeholders approvals | Project manager | 2 | Get approvals for BluePrint documents based on business processes
Realization phase Deliverables: SIT & UAT scripts & SIT sign offs | 2.1 | System and Module Configuration | 2.1.1 | system installation,configuration and settings | Technical Lead | 20 | System installation ,Settings configuration: including the setup of system parameters, user roles, and security settings.
|  |  | 2.1.2 | Configure system functional modules | Functional Team | 25 | Configure Functional modules based on business processes
|  |  | 2.1.3 | Develop customizations and integrations | Techincal Team | 15 | Develop custom code and integrations for the system, including the development of custom reports, interfaces, and workflows.
| 2.2 | Data Cleansing | 2.2.1 | Master data cleansing by using data management tools | Data Specialist | 30 | Removing, inconsistencies, duplications, and missing entries from data to increase data consistency and quality
|  |  | 2.2.2 | Communicate data cleasing results with IT team and stakeholders | Data Specialist | 60 | communicate data cleasing results
|  |  | 2.2.3 | Prepare Sample Upload for testing |  | 10 | use Master data sample in SIT test
| 2.3 | Functional testing | 2.3.1 | Conduct unit testing and debugging | Quality Assurance team | 10 | Conduct unit testing and debugging of the system, including the testing of custom code and integrations.
|  |  | 2.3.2 | Develop test plans and scripts | Quality Assurance team | 5 | Develop test plans and scripts for the system, including the testing of system functionality and integration.
|  |  | 2.3.3 | Conduct system testing and quality assurance (SIT) | Fuctional team | 10 | Conduct system testing and integration testing of the system, including the testing of system functionality and integration.
|  |  | 2.3.4 | Identify and resolve defects | Techincal team | 5 | resolves bugs and defects results from user testing
| 2.4 | Infrastructure and Hardware procurement | 2.4.1 | Tender for hardware and data storage vendors | Procurement team | 10 | communicate with vendors for creating tender for procurements of hardware and data storage
|  |  | 2.4.2 | complete Infrastructure and Hardware procurement process | Procurement team | 45
Final Preparation & User training Deliverables: UAT signoffs Training manuals | 3.1 | User Acceptance Testing | 3.1.1 | Conduct user acceptance testing workshops (UAT) | Fuctional team | 10 | Conduct system testing with key users to ensure business requirements are met
|  |  | 3.1.2 | Get Final approvals for (UAT) | Project manager | 5 | Get final approvals from stakeholders
| 3.2 | Key users Training | 3.2.1 | Develop user manuals and training materials | Training Team | 15 | Develop training materials & quick videos for end users
|  |  | 3.2.2 | Conduct Key-user training and support | Training Team | 20 | Conduct end-user training and support for the system, including the training of Key-users on system functionality and usage.
Go-Live,Deployment & Post-Implentation support Deliverable : System deployement to production | 4.1 | System Go-Live Preparation | 4.1.1 | Finalize Cutover Plan | Project Manager | 5 | schedule execution of the go-live activities for the system, including the deployment of the system to production ,Procurement,training,completed & all aprprovals signed
|  |  | 4.1.2 | Execute Go-Live Checklist | Project Manager | 5 | ensure a smooth transition from the implementation phase to operational use of the system check testing sig off, documentations finalized, training completed,system readiness,
| 4.2 | Go Live & Support | 4.2.1 | System deployment to production | Techincal team | 10 | Set up the production environment & final configurations and settings
|  |  | 4.2.2 | Master data and opening balances upload | Functional team | 5 | system deployment to production, including master data & opening balances upload
| 4.3 | Post Go Live support | 4.3.1 | Conduct post-go-live support and monitoring | Project Manager | 90 | Conduct post-go-live hyper care support and monitoring for the system, including the resolution of technical issues and bugs.
PetroPower Refinery
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Serve OKR 2 (Data efficiency)
Note on E16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Serve OKR 2 (Data efficiency)
Note on E28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: OKR 3 (Training and support)
Note on E29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: OKR 3 (Training and support)